## Cover Page
Auto Identification System
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Academy - Project Solutions
Role
Signature
Date
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions Project ID: <Batch code/project id> C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog Auto Identification System Project ID: A018 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Priority | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Role Selection | AIP Admin/Bank Employee | Ability of the system to allow a user to choose the required User role for registration | 1. When a visitor opens the web page, the initial screen should display the options to select from the different roles to which a user would like to register. 2. The roles to be displayed as "AIP Admin" or "Bank Employee" The user have to select the roles to login. If AP Admin is selected redirect to Login Page. If bank employee is selected, redirect to login page and have a link as below. New User - Register. Clicking Register should redirect to employee registration page. | Critical
US_2 | Employee Registration | Bank Employee | As a user, I should be able to register to this website | 1. Clicking on the “Register” button should open the Registration form. 2. User to fill the basic profile attributes: First Name Last Name DOB Gender (radio button) Contact Number City State (drop down) User Id (Auto generated) Password Name should be in range 4-50 DOB should be entered and the age should not be less than 18. Contact number should be of 10 digits Password should be of minimum 6 letters with special characters included. Note - Trainees can add/neglect fields that will be appropriate and validations should be handled for all fields 3. Clicking ‘Submit’ button should validate the datatype constraints for each field 4. User failing to provide information for the mandatory fields be presented with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5. Post-successful field validation, save the information in the database 6. Upon saving the information in the database, display the message “New user created successfully” Note - Use drop downs, radio buttons, checkboxes wherever applicable | Critical
US_3 | Employee Authentication | Bank Employee | As a user, I should be able to log in | 1. A registered user – is able to click ‘Login’ link, after keying in ‘User ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. 2. A user whose registration is rejected – is unable to login and get the credentials authenticated, the user is presented with relevant error messages: Invalid User ID (or) Incorrect Password | Critical
US_4 | Admin Registration | AIP Admin | As an Admin, I should be able to register | 1-Users should have option to select their role option 2-Admin should select the Admin option. 3-Admin's User id and password should be pre-loaded in the database, which can be used to log in. | Critical
US_5 | Admin Authentication | AIP Admin | As an Admin, I should be able to log in | 1. A registered user – is able to click ‘Login’ link, after keying in ‘User ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. 2. A user whose registration is rejected – is unable to login and get the credentials authenticated, the user is presented with relevant error messages: Invalid User ID (or) Incorrect Password | Critical
US_6 | Customer Database | System | Allows the system to store the customer details along with their loan, payments and dues | 1. The customer details along with the load details, payment date, payment status, dues, late fee etc should be mocked up and saved to the DB. Note: this is a stand alone application and hence the required data to run this application needs to be mocked up.
US_7 | Auto Defaults | AIP Admin | Allows the admin to generate the list of auto defaulters | 1. Once the AIP Admin logs in, he should be able to view the list of Auto Defaults. 2. Before displaying auto defaulter’s data admin needs to know the users who are defaulters and out of them those who fall under auto defaulter criteria 3. After admin loads the defaulter’s data in a table, based on the Borrower Rating and Accrual Status of the data, defaulters to be classified into auto defaulters. 4. Borrower Rating greater than or equal to 8 and Accrual Status (2 or 3 or 4 or 5) shall come under auto default. 5. Any given point of time, the AIP Admin should have the option to go for home page, by clicking home. | Critical
US_8 | Manual Defaults | AIP Admin | Allows the admin to generate the list of auto defaulters | 1. Once the AIP Admin logs in, he should be able to view the list of Manual Defaults. 2. Before displaying Manual defaulter’s data admin needs to know the users who are defaulters and out of them those who fall under Manual defaulter criteria 3. After admin loads the defaulter’s data in a table, based on the Borrower Rating and Accrual Status of the data, defaulters to be classified into manual defaulters. 4. Borrower Rating greater than or equal to 5 and less than 8 or Accrual Status as 1 or 6 or 7 and DPD (Days Past Due) >= 90 shall come under Manual default 5. Any given point of time, the AIP Admin should have the option to go for home page, by clicking home. | Critical
US_9 | Updating Defaults Status | AIP Admin | Allows the admin to update the defaults list based on their DPD | 1. Once the Manual/Auto defaulters list is generated by the admin, admin to have the authority to change the defaulter status of any borrower saved in the database 2. If the borrower is regularly paying the dues and is no longer called a defaulter then admin should update the default status as Validate Error since the customer record should not be shown in the list 3. If the borrower pays the dues but not on time and is irregular in terms of his payment, then admin should update the default status as Auto Waver. 4. Admin to update comments for the updates, and save the changes. 5. Portal to save the changes to the database and display a message “Changes saved successfully” | Critical
US_10 | Send Reminders | AIP Admin | Portal to send reminders to the defaulters for repayment and the amount pending | 1. Admin to generate a list of defaulters who have not paid their dues for more than 6 months from the current day 2. Portal to display a page with the requested list and a button called “Send Reminder” for each defaulter 3. Portal to procure the defaulters contact information saved in the database and display the report. Note - reminders can be displayed in the home page/Notification page. as we dont have SMTP server access to send remainders. | Critical
US_11 | Customer Details | Bank Employee | Application to allow the bank representative to see the list of Customers who are defaulters and their details saved in the database | 1. Once the bank representative logs in to the application, the application should display a page with the complete list of defaulters. 2. Once a particular user is selected, the complete details of the user profile should be displayed 3. Based on the dues interval, user should receive a message on cancellation of their card. Note - Use pagenation while listing . Message cannot be sent to the customer hence update the status and maintain in the DB. | Critical
US_12 | Dues Interval Action | Bank Employee | Take action for dues based on the interval considering disputes raised by customer. | 1. System to calculate the total interval of the dues for each type of defaulter 2. Carry different functions for each interval of dues: --> Due upto 3 months - Late payment charges --> Due more than 3 months, less than 6 months - Send reminders/notifications once a week --> Dues for more than 6 months, less than 12 months - Card to be blocked and user should not be allowed to use, however user can get it activated by completing the dues --> Dues for more than 12 months - Card should be auto cancelled and user cannot re-activate the card. Note: Mock up data for Customer disputes and this has to be handled by the bank employee while processing Dues | Critical
US_13 | Card Re-Activation | Bank Employee | Application to provide an option for the bank representatives to Re-activate the card | 1. Application to capture the payments made by the customer and save the details in the database 2. Application to calculate the current status of the customer payments. 3. Incase the customer has paid the late payment fees and outstanding charges, the Bank employee to be allowed to re-activate the card. 4. Selecting a single customer profile should open a new page with only the below details: Customer Name Account Number Card Number Date Re-activation Reason Note: Data mock up to be done for payments made by the customer and based on the data, cards can be re activated. | Critical
US_14 | Updating/modifying Status | Internal Function | In case of re-activation, system to update the defaulters list accordingly | 1. Application to allow the bank representative to edit or modify the defaulters list 2. System to allow the bank representative to manually update the defaulters status and update the card details. | Medium
US_15 | Notification | Internal Function | Application to send notification to the customers about the re-activation processed | 1. Post the pending payments are cleared and Bank representative re-activates the card, Application to retrieve the customer contact details and send an email/SMS to the registered contact information. 2. Post the notification is sent successfully, update the database with the re-activation status Note: we do not have access to SMTP server to send SMS/ message. Just update the status in the DB. | Medium
US_16 | Generate report | AIP Admin | As an AIP Admin, I should be able to generate a report to view the defaulters | 1. AIP Admin On clicking Generate report, it should display the below options. No. of defaulters No. of Re-activation requests No. of Auto Defaulters No. of Manual Defaulters 2. On selecting the option, it should pull report from the Database 3. AIP Admin to be allowed to sort the details for each of the field available in the report | Medium
US_17 | Other validations | AIP Admin/Bank Employee | Ability of the system to allow add on validations like Forgot Customer ID, Forgot Password | 1. During registration, System should pop up three secret questions for Password recovery. 2. When the user clicks Forgot User ID, system should ask for the secret questions. On answering the questions correctly, the User ID should be displayed. 3. When the user clicks Forgot Password, system should ask for the User ID and secret questions,Email id, Mobile number. On answering the questions correctly, the password reset page should be displayed. 4. On entering the details in the password reset page, password should be validated 5. On clicking Submit, the details should be saved to the Database | Low
US_18 | User logoff | AIP Admin/Bank Employee | Ability of the system to allow the user to logoff | 1. Option to log off from the system. | Critical

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000